## Sheet1
List of remaning work to be done on compu c website

Job	Language	Allocated person
shop.html: working links to display only one type of product at a time (could re-use menubar CSS?)	Javascript/CSS	Laura
index.html: could do with another segmentDiv or two of...something...idk	HTML	Laura
all pages: compu c picture header shows up as different sizes on some pages, investigate and fix that	HTML (?)	Ronan	FINISHED
myDetails.html: finish off login/signup/edit details	Javascript	Ronan	FINISHED
all pages: tweak style until satisfactory (eg. h1/h2/… headings have too much top/bottom padding and too little left/right padding)	CSS	Ronan
all pages: add login box to top right of all pages	Javascript/HTML	Ronan	FINISHED
cart.html: add ability to purchase the list of goods in the cart	Javascript	Tommey
cart.html: Display chosen products	Javascript	Tommey